## Sprint Planning
# | Epic | User Story | Team Capacity | Estimated Time (In hours) | Assign To
1 | Create Account | As a user, I want to create account so that I can start to use the application | 1 | 6
As an admin, I want to ask users for their credientails so that to create and verify the user login data in the system
2 | View Restaurants | As a user, I want to see restaurants' list so that I can select the desired type of restaurants | 2 | 7
As an admin, I want to create a list of restaurants so that user can see all available restaurants
3 | Search Restaurants | As a user, I want to search for a specific restaurant so that I can see its menu and order from | 2 | 8
As an admin, I want to set a search box in the main page so that enabling user to search for their faviourt restaurant
4 | View Menu | As a user, I want to see the menu of the selected restaurant so that I can order the desired meal | 2 | 7
As an admin, I want to insert the menu under each resturant so that the user can select their meals
5 | Add to Cart | As a user, I want to save the selected meals in a cart so that I can review all the selected meals before ordering | 2 | 8
As an admin, I want to move and save the selected meals in to his cart so that the user can proceed the ordering
6 | Purchase | As a user, I want to pay for selected meals so that to receive the order | 1 | 10
As an admin, I want to calculate the fees of the meals in the cart so that asking user to pay this amount
7 | Restaurant views order | As a restaurant, I want to receive a notification by the order so that I can prepare it on time | 1 | 10
As an admin, I want to send the order to the assigned restaurant so that the restaurant prepare to deliver to user
8 | Restaurant marks order as delivered | As a user, I want to track my order so that I can be ready to collect the order | 1 | 18
As an admin, I want to connect the so that the user can track the delievry process
74