## Task Board
TASK BOARD
EPIC | Sprint Duration | TO DO | IN PROGRESS | TESTING | DONE
Create Account | 8 days | 5- User credientails verifications | 4- Applying restrictions to required fields | 2- Password security check 3- Check for duplicated or existing data on DB | 1- Sign up form design
View Restaurants | 4 days | - | 4- Calling data from the database | 3- Check the command fields | 1- Create form of the search page 2- Template of results
Search Restaurants | 3 days | 3- Build the search algorithms | 2- Identify the keywords of the searchable words in the search bar | 1- Search bar design | -
Sprint 1: Create Account | [5 empty] | Sprints
Task Name | Planned Duration | Actual Duration | Planned Remaining Days | Actual Remaining Days |  | Sprint # | Sprint Name | Planned Duration | Actual Duration | Planned Remaining Days | Actual Remaining Days
Sign up form design | 2 | 3 | 6 | 8 |  | 1 | Create Account | 8 | 11 | 7 | 6
Password security check | 1 | 1 | 5 | 7 |  | 2 | View Restaurants | 4 | 4 | 3 | 2
Check for duplicated or existing data on DB | 2 | 3 | 3 | 4 |  | 3 | Search Restaurants | 3 | 2 | 0 | 0
Applying restrictions to required fields | 1 | 1 | 2 | 3 |  |  |  | 15 | 17
User credientails verifications | 2 | 3 | 0 | 0
| 8 | 11